## WBS
ID | Phase | Task | Sub-task | Responsibility | Estimated Effort (MD) | Start Date | End Date | Status
1 | Project Management | Overall Mgmt | Project Kickoff | PM | 0.5 | 2026/05/12 | 2026/05/12 | Done
1.1 |  |  | Weekly Status Report | PM | 2 | 2026/05/12 | 2026/08/08 | Ongoing
2 | Design & Setup | Requirements | Finalize CSV Mapping | Engineer | 1 | 2026/05/12 | 2026/05/16 | Done
2.1 |  | Design | Library-based Arch Design | Lead | 2 | 2026/05/12 | 2026/05/16 | Done
2.2 |  | Environment | Setup Test Domain/API Keys | Engineer | 1 | 2026/05/19 | 2026/05/20 | To Do
3 | Shared Library | Auth | rakumo HMAC-SHA1 Module | Engineer | 1 | 2026/05/19 | 2026/05/23 | Done
3.1 |  | Core | API Client (Retry/Logging) | Engineer | 1 | 2026/05/19 | 2026/05/23 | Done
3.2 |  | GWS API | Admin SDK Users/Groups Wrapper | Engineer | 2 | 2026/05/26 | 2026/05/30 | Done
3.3 |  | rakumo API | Profile/Sync API Wrapper | Engineer | 2 | 2026/05/26 | 2026/05/30 | Done
4 | Tool 3 (Integrated) | UI | Integrated Dashboard Sheet | Engineer | 2 | 2026/06/02 | 2026/06/13 | To Do
4.1 |  | Logic | Sync Workflow Implementation | Engineer | 3 | 2026/06/16 | 2026/06/27 | To Do
4.2 |  | Process | Batch Processing (6min limit) | Engineer | 2 | 2026/06/30 | 2026/07/03 | To Do
5 | Derivation | Tool 1 | rakumo-specific UI/Logic | Engineer | 1.5 | 2026/07/14 | 2026/07/21 | To Do
5.1 |  | Tool 2 | GWS-specific UI/Logic | Engineer | 1.5 | 2026/07/14 | 2026/07/21 | To Do
6 | Testing | Unit | Library Module Testing | Engineer | 2 | 2026/07/07 | 2026/07/11 | To Do
6.1 |  | Integration | Tool 3 E2E Testing | QA | 3 | 2026/07/14 | 2026/07/18 | To Do
7 | Delivery | Docs | User Manual (3 tools) | Writer | 3 | 2026/07/21 | 2026/08/01 | To Do
7.1 |  | Release | Final Handover | PM | 1 | 2026/08/04 | 2026/08/08 | To Do